## Status
PROJECT NUMBER	SSAD-32
PROJECT NAME	Mystique
PROJECT MENTOR (sponsor)	Ashwini Patankar

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (August 7- August 13)
Fix meeting with client	Coordination	Saketh	0.5	0.5	Done		0	0
GIT Repository setup	Preparation	Kamal	1	1.2	Done		-0.2	16.6666666666667
Client meeting	Coordination	Preetham	1	0.7	Done		0.3	42.8571428571429
Create Trello and Bluemix accounts	Preparation	Preetham	1	0.8	Done		0.2	25
Research existing technology	Preparation	Kamal	4	4.5	Done		-0.5	11.1111111111111
Project synopsis writeup	Documentation	Saketh	1	1.25	Done		-0.25	20
Identify role owners	Preparation	Kamal	1	0.6	Done	Getting to know about the company	0.4	66.6666666666667
Team Meeting	Preparation	Saketh	1	1.2	Done	Discussion about cllient meeting	-0.2	16.6666666666667
Status tracker	Documentation	Preetham	1	0.6	Done		0.4	66.6666666666666
Week 2 (August 14 - August 20)
Research on blockchain	Preparation	Kamal	4	3.5	Done		0.5	14.2857142857143
Research on visualizing cryptocurrency using blockchain	Preparation	Saketh	3	3.2	Done		-0.2	6.25000000000001
Team Meeting	Preparation	Preetham	0.5	0.5	Done	Discussion about technologies found till now	0	0
Report to visualize blockchain using Vivagraph	Documentation	Saketh	2	1.5	Done		0.5	33.3333333333333
Installing Hyperledger and blockchain	Preparation	Preetham	4	4.5	Done		-0.5	11.1111111111111
Team Meeting	Coordination	Kamal	0.5	0.75	Done	Distribution of work among team members	-0.25	33.3333333333333
Status tracker	Documentation	Saketh	0.5	0.25	Done		0.25	100
Fix meeting with client	Coordination	Preetham	0.25	0.25	Done		0	0
Client meeting	Coordination	Saketh	1	1	Done		0	0
Report to visualize blockchain using D3	Documentation	Kamal	2	2	Done		0	0
Week 3 (August 21 - August 27)
Fix meeting with client	Coordination	Preetham	0.2	0.1	Done		0.1	100
Client meeting	Coordination	Saketh	0.5	0.75	Done		-0.25	33.3333333333333
Team Meeting	Preparation	Kamal	0.5	1	Done		-0.5	50
UI Model Design	Documentation	Kamal	4	3	Done		1	33.3333333333333
Research on existing UI’s for designing layout of the framework	Documentation	Saketh	3.5	3.25	Done		0.25	7.69230769230769
Searching for the softwares suitable for the project	Preparation	Preetham	2.5	2	Done		0.5	25
Week 4 (August 28 - September 3)
Fix meeting with client	Coordination	Preetham	0.1		Planned
Client meeting	Coordination	Saketh	0.5		Planned
Team Meeting	Preparation	Kamal	0.75		Planned
Use cases	Documentation	Saketh	3		Done
User stories	Documentation	Kamal	3.5		Ongoing
Learn PlantUML	Preparation	Preetham	4		Done
Week 5

Week 6

## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	SSAD-32
PROJECT NAME	Mystique
PROJECT MENTOR (sponsor)	Ashwini Patankar
TEAM MEMBERS	Sathineni Preetham Reddy
	K L N Saketh
	Amuluru Sai Kamal
	Team Member Name 4
	Team Member Name 5